## Week 1
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 1
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Proposal and Statement of Work (All) - 6 hours | 6
- Data Collection (minus DB polygons) (All) - 8 hours | 8
- General Transit Feed System (GTFS) - 10 hours | 10
- Setting up our project page on Taiga.io (All) 2 hours | 2
- First client meeting and project overview - 1 hour | 1
TOTAL | 27
ADDITIONAL COMMENTS

## Week 2
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 2
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Updated the CDB data wrangling file to output a CSV with standardized column names (Graham) - 2 hours | 2
- Discussed and planned out the high level data manipulation and score computing (All) - 6 hours | 6
- CDB and ODACF data filtering (Graham + Rain) - 8 hours | 8
- Develop time matrix using R5 (All) - 8 hours | 8
- Discussed method to develop score computations (All) - 8 hours | 8
- Weekly presentation (All) - 3 hours | 3
TOTAL | 35
ADDITIONAL COMMENTS

## Week 3
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 3
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Created visualization of scores in Vancouver using python (Graham) - 6 hours | 8
- Researched R Shiny and Dash for dashboard visualizations (Graham) - 3 hours | 6
Weekly Presentation | 3
TOTAL | 17
ADDITIONAL COMMENTS
Large number of interviews and interview preparation

## Week 4
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 4
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Created an outline for the final report (All) - 1 hour | 1
- Worked on deploying draft dashboard (Graham) - 25 hours | 25
- Team meeting and presentation preparation (All) - 3 hours | 3
TOTAL | 29
ADDITIONAL COMMENTS

## Week 5
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 5
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Worked on deploying dashboard (Graham) - 8 hours | 8
- Added Kepler to dashboard (Graham) - 1 hour | 8
- Researched methods to calculate transit efficiency scores (Graham + Luka) - 8 hours | 8
- Converted dashboard to use HTMLs instead of Leaflet maps // Dashboard performance upgrade: added feature to call on pre-rendered HTML maps as opposed to performing computations on the fly (Luka + Graham) - 20 hours | 15
- Prepared presentation slides (All) - 3 hours | 3
- Mid-term presentation (All) - 8 hours | 8
TOTAL | 50
ADDITIONAL COMMENTS

## Week 6
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 6
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Report writing (All) - 20 hours each | 20
- Developed first iteration of the efficiency model and maps (Graham) 16 hours | 16
- Wrote method-dashboard section of the report (Graham) - 8 hours | 8
- Recomputed travel time matrix, scores, and fresh HTML maps using the merged code with the most recent scoring function (check to see if all code is still functional) (All) - 6 hours | 6
TOTAL | 50
ADDITIONAL COMMENTS

## Week 7
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 7
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Created ggplot2 violin plot visualizations (Luka + Graham) - 2 hours | 2
- Code review to complete the efficiency model and visualizations (Graham + Luka) - 4 hours | 4
- Weekly presentations (All) - 3 hours | 3
Changed efficiency model and maps (Graham) - 8 hours | 15
- Report writing/presentation (Graham & Rain) - 15 hours | 15
TOTAL | 39
ADDITIONAL COMMENTS

## Week 8
<NAME>
2020.05.04
Master of Data Science Capstone Project - 2021 |  | Week #
University of British Columbia - Okanagan |  | 8
Kelowna, BC
CLIENT
Graham Kerford
DESCRIPTION | HRs
- Code documentation and Readmes (All) - 5 hours | 5
- Changed efficiency model and maps (Graham) - 8 hours | 8
- Report writing (All) - 20 hours each | 20
- Presentation (All) - 15 hours | 15
- Fixed dashboard layout/display (Graham) - 2 hours | 2
- Added draggable titles and page descriptions to the dashboard (All) - 4 hours | 4
TOTAL | 54
ADDITIONAL COMMENTS